## 1 · README
📊 Build Sprint · Day 6 · 24-Day Project Plan
From today (Day 6 · Mon 8 Jun) to Public Pitch Day (Day 29 · Mon 29 Jun)
Welcome, builder.
This plan IS your contract for the next 24 days. Open it Monday morning. Read the day's deep block. Do the work. Mark % done. When you slip — the slip indicators tell you what to cut.
⚡ How this workbook works
1. Tab 2 · Setup — name yourself, your product, your start date. Auto-calculates dates across tabs 3-7.
2. Tab 3 · Weekly Milestones — 3 milestones per week. Pre-loaded. Edit if you want.
3. Tab 4 · Daily Plan — your 2-hour deep block + secondary task for each of 24 days.
4. Tab 5 · Slip Indicators — what to cut when something slips. Read these before the week starts.
5. Tab 6 · Progress Dashboard — % complete · days remaining · risk indicator (auto-calculated).
6. Tab 7 · Weekly Digest — paste-ready text for your Sunday cohort post.
⚓ Cal Newport's 4 non-negotiables baked in
1. One 2-hour deep block per day. No exceptions.
2. Each week has EXACTLY 3 milestones — no scope sprawl.
3. Slip indicators are pre-set — if you slip, the cut is decided in advance (no emotional debate).
4. Sunday weekly digest is paste-ready — you commit publicly to next week, not just to yourself.
Build Sprint · 30daystoship.com · Network School

## 2 · Setup
⚙️ Setup — fill these once
All other tabs reference these values. Change them here and they flow through.
Your name | Megan Martinsone
Product name | Your product name
The ONE feature | e.g., Upload 3 articles → get next in your voice
Target user | e.g., Freelance writers behind on their content calendar
Start date (Day 6) | 2026-06-08
Public Pitch Day | 2026-07-01
Daily deep hours | 4
Email signups so far | 0
Public commit (1 sentence) | By Day 30 I ship [feature] for [user] with [N] users.

## 3 · Milestones
🎯 Weekly Milestones
3 milestones per week. Already pre-loaded. Edit dates from Setup tab — they auto-cascade.
Week | Milestone | Target date | Done when | % done
W2 · BUILD | M1 · Lovable scaffold + Supabase wired | 2026-06-14 | Live URL with 3 screens (Entry · Working · Aha) | 0%
| M2 · The ONE feature works end-to-end | 2026-06-17 | Stranger can use it without a tour | 0%
| M3 · 5 internal testers logged in | 2026-06-20 | 5 test accounts in Supabase + 3 verbatim feedback notes | 0%
W3 · SHIP | M4 · Custom domain + analytics live | 2026-06-21 | Plausible firing + custom domain in DNS | 0%
| M5 · 25 real users on the product | 2026-06-24 | 25 unique user_id rows in Supabase | 0%
| M6 · 10 user-test recordings reviewed | 2026-06-26 | 10 Loom or Granola recordings + 3 changes shipped | 0%
W4 · SELL | M7 · Pricing live in Stripe | 2026-06-28 | Test card buys successfully | 0%
| M8 · Sellathon: 50 cold outreach + 5 trials | 2026-06-30 | 50 messages sent + 5 trial signups | 0%
| M9 · 100 active or paying users | 2026-07-01 | 100 user_id rows · 1+ paid | 0%
W5 · PITCH | M10 · Pitch deck v1 (Sequoia format) | 2026-06-25 | 10 slides · 1 dry-run with pod buddy | 0%
| M11 · Recorded pitch (5-min) | 2026-06-30 | Self-recorded · uploaded · cohort review | 0%
| M12 · Public Pitch Day · LIVE | 2026-07-01 | Pitched live · award attempt · Discord post | 0%
TOTAL |  |  | Overall completion: | 0%

## 4 · Daily Plan
📅 Daily Plan · 24 days
Day 6 (today) → Day 29 (Public Pitch). 2-hour deep block + secondary task per day. Mark ✓ when done.
Day | Date | Deep block (2 hr) | Secondary task | ✓
6 | 2026-06-08 | Run Prompt 05 in Lovable · scaffold 3 screens | Supabase tables + RLS · test login
7 | 2026-06-09 | Vibe-coding session (Day 7) · build Screen 1 | Connect auth to Supabase
8 | 2026-06-10 | Build Screen 2 · the ONE feature | Write empty + error states
9 | 2026-06-11 | Build Screen 3 · the Aha moment | Wire share button + clipboard
10 | 2026-06-12 | Polish · deploy to lovable.app | Test on phone · fix mobile bugs
11 | 2026-06-13 | 5 internal user tests (live with pod) | Note 3 verbatim quotes
12 | 2026-06-14 | Apply 3 fixes from feedback | Sat showcase prep
13 | 2026-06-15 | Custom domain + Plausible analytics | Tweet "shipping today" · cohort post
14 | 2026-06-16 | Public launch · post to Reddit + HN | Reply to first 5 comments
15 | 2026-06-17 | User test session #2 (5 strangers) | Identify the 1 biggest friction
16 | 2026-06-18 | Fix the #1 friction point | Tighten the hero · 1 word change
17 | 2026-06-19 | Cohort wall post · ship a metric update | Email signups follow-up
18 | 2026-06-20 | Sat hackathon: 24-hr growth sprint | +25 net new users target
19 | 2026-06-21 | Rest. Cohort applause beat. | Post your week 3 numbers
20 | 2026-06-22 | Wire Stripe · pricing live | Test card buys successfully
21 | 2026-06-23 | 🔥 Sellathon Day · 4-hour blitz | Cold outreach · LinkedIn + email
22 | 2026-06-24 | Reply to all trial signups personally | Onboarding loom for each
23 | 2026-06-25 | Pricing experiment · A/B headline | Update copy from sellathon learnings
24 | 2026-06-26 | Showcase #3 prep · 100-user demo | Pitch dry-run with pod buddy
25 | 2026-06-27 | Sat hackathon: Ship & Tell finale | Polish v1.5 feature + campaign
26 | 2026-06-28 | Sun: Cohort breakfast · rest | Print pitch deck · final review
27 | 2026-06-29 | Pitch rehearsal · 3x cold reads | Time 5 min · cut if over
28 | 2026-06-30 | Pitch rehearsal #2 · cohort + judges | Get 1 brutal critique · fix it
29 | 2026-07-01 | 🌟 Public Pitch Day · 14:00–18:00 | Celebrate · alumni induct · DM post
|  | Days completed: | 0 / 24

## 5 · Slip Indicators
🚨 Slip Indicators · the cuts decided in advance
Read these BEFORE the week starts. When a milestone slips, the cut is pre-decided — no emotional debate at 23:30 on a Friday.
If milestone | Slips past | Then cut
M1 · Lovable scaffold | Day 6 EOD | Empty/error states from v1. Build them after testers, not before.
M2 · The ONE feature E2E | Day 9 | The ENTIRE Aha screen polish. Default success state = plain text + button.
M3 · 5 internal testers | Day 12 | Friday showcase prep. Use the time to find testers instead.
M5 · 25 real users | Day 16 | Custom domain (lovable.app URL is fine for v1). Focus on growth.
M7 · Pricing live | Day 20 | Pricing page polish. Use Stripe Payment Link only.
M9 · 100 users | Day 23 | Goal becomes "qualitative win" — 10 thrilled users beats 100 lukewarm.
M10 · Pitch deck | Day 23 (W5) | Animations / illustrations. Plain text deck > Beautiful empty deck.

## 6 · Dashboard
📈 Progress Dashboard
Live view. Auto-updates as you tick off milestones and daily tasks.
Days into the sprint | 0
Days remaining to Pitch Day | 1900-01-23
Milestones completed (of 12) | 0
Overall milestone % complete | 0%
Daily tasks completed (of 24) | 0
Current week | W1
Email signups (so far) | 0
🚦 Status
Expected progress | 0%
Actual progress | 0%
Risk indicator | ✅ ON TRACK

## 7 · Weekly Digest
📨 Weekly Digest · paste-ready cohort post
Fill in once per week (Sunday) · copy · paste into cohort Discord/Slack.
🎯 BUILD SPRINT · WEEK [N] DIGEST · [@your-handle] This week I shipped: • [milestone 1] • [milestone 2] • [milestone 3] Numbers: • Users: [N] • Email signups: [N] • Hours of deep work: [N] What surprised me: [1-2 sentences — the genuine learning, not the polished take] What I'm cutting next week: [1 thing you're publicly cutting · the slip indicator move] What I'm shipping next week: [1 milestone · 1 date · 1 done-criterion] The hero line still holds: [your hero] #buildsprint #day[N] #30daystoship
⚡ Pro tip · the public commit is the contract
Posting the digest publicly each Sunday is what turns a private plan into a real ship date. The cohort holds you to last week's post. The slip indicators tell you what to cut when something slides.